## Sheet1
Req ID | Description | Story Points | Priority | Sprint No.
1 | Spike: Research Google Maps API capabilities & pricing | 5 | 1 | 1
2 | Spike: Research restaurant & deals APIs (Yelp, Groupon, etc.) | 5 | 1 | 1
3 | Display Google Map centered on user location | 8 | 3 | 1
4 | Fetch nearby restaurants from Google Maps API | 8 | 3 | 1
5 | Display restaurant markers on map | 5 | 3 | 1
6 | Show restaurant info popup (name, rating, cuisine) | 3 | 3 | 1
7 | Basic Supabase project setup (DB + config) | 3 | 3 | 2
8 | Add deals functionality | 5 | 3 | 2
9 | Error handling for failed API calls | 3 | 5 | 2
10 | Display deals in restaurant popup | 3 | 5 | 2
11 | Search restaurants by name | 3 | 5 | 2
12 | User sign up and login | 5 | 5 | 2
13 | Display restaurants with deals by using custom marker | 2 | 6 | 3
14 | Implement a side bar with list of restaurants | 5 | 6 | 3
15 | Sort by restaurants by distance | 8 | 6 | 3
16 | Ensure restaurants that have deals are on the top of list view | 3 | 6 | 3
17 | View list of saved favorite restaurants | 3 | 7 | 3
18 | Save restaurant as favorite | 5 | 7 | 3
19 | User profile page (view saved data) | 3 | 7 | 3
20 | Persist favorites in Supabase database | 3 | 7 | 3
21 | Filter restaurants by cuisine | 3 | 8 | 4
22 | Filter restaurants by distance | 3 | 8 | 4
23 | Filter restaurants by price range | 3 | 8 | 4
24 | Filter restaurants by rating | 3 | 8 | 4
25 | Responsive layout for mobile and desktop | 5 | 20 | 4
26 | Loading indicators while fetching data | 2 | 20 | 4
27 | Persist selected filters during session | 3 | 20 | 4
28 | Final UI polish and usability improvements | 5 | 20 | 4
29 | Integrate deals API with restaurant data | 8 | 20 | 4
30 | Spike: Research React Native/Expo for mobile migration | 3 | 1 | 5
31 | Initialize Expo React Native project | 5 | 1 | 5
32 | Display interactive map with user location (mobile) | 8 | 3 | 5
33 | Fetch and display nearby restaurants on map (mobile) | 8 | 3 | 5
34 | Restaurant detail modal (mobile) | 5 | 5 | 5
35 | User authentication — login and signup (mobile) | 5 | 5 | 5
36 | Basic restaurant filters — cuisine, distance, price, rating (mobile) | 5 | 5 | 5